## LMS-Plan
Implemetation Schedule of Litigation Management System (LMS) BRAC Bank Limited
INITIATED: June 22, 2021 | [6 empty] | TARGET END: TBD
SL | Milestones | Responsible Party(s) | Work Breakdown Structure | Schedule |  |  | Remarks
|  |  |  | Planned End Date | Actual End Date | Actual % Work Progress
1 | Kick-off | MICROMAC, BBL | Initial discussion about project planning | 2021-06-22 | 2021-06-22 | 100%
2 | Requirement Gathering and Analysis | MICROMAC, BBL | Functional DRG-1 | 2021-07-29 |  | 100%
|  |  | Functional DRG-2 |  |  | 100%
|  |  | Alignment Session within BBL(Legal-1) |  |  | 100%
|  |  | Functional DRG-3 |  |  | 100%
|  |  | Functional DRG-4 |  |  | 100%
|  |  | Alignment Session within BBL(Legal-2) |  |  | 100%
|  |  | Functional DRG-5 |  | 31-08-2021 | 100%
|  |  | Functional DRG-6 |  |  | 100%
|  |  | Functional DRG-7 |  |  | 100%
|  |  | Technical DRG-1 |  |  | 100%
|  |  | Technical DRG-2 |  | 2021-08-16 | 100%
3 | FSD Preparation | MICROMAC | FSD preparationby Micromac and reviewed & Acknowledged by BBL | 2021-08-12 | 2021-08-19 | 100%
4 | FSD Sign-off | BBL & Micromac | • For quick project delivery (phase-1), go-ahead given by BBL | 2021-08-19 | 2021-08-19 | 100% | Pending, bank is requested to shar the FS sign-off date
|  | BBL | • Internal Sign-off is going on(ICC,ORM,IS,Legal are already given) | 2021-10-20 |  | 50% | Need to work against feedback received from various stakeholders
5 | 1st Phase Deliverables: - Legal Notice - Case Merit Analysis Approval (with auction feature) | BBL(Core System -Aman) | UAT Environment Readiness :: Application Server Readiness Test Server details: IP:172.25.5.28 Hostname: cms-poc OS:RHEL 7.8 /Apache Directory: /app Port Details: • 4009 [MySQL] • 8085 [HTTP] • 22 [SSH, SCP, SFTP] | 2021-09-30 |  | 100% | As per bank decision the POC server will be used as UAT server.
|  | BBL(IS-Shaila, Core System-Ranju) | UAT Environment Readiness :: Application Server Readiness VA & Mitigation: Phase-1: 13 Phase-2: 3 Phase-3: 0(Completed) | 2021-09-30 | 2021-09-14 | 100% | VA shared by IS team & Mitigated by Core System team.
|  | BBL(DBA-Nasim) | UAT Environment Readiness :: Database Server Readiness DB Server details: DB Name: lmsdb Username: lms DB IP: 172.25.15.121 DB Port: 3489 | 2021-09-13 | 2021-09-13 | 100% | DB is hosted in separate server
|  | BBL(Network-Sezanur, DBA- Nasim) | Landing PC to Server Connectivity :: - 10.5.9.20(LPC) to 172.25.5.28(App Server) Network level - 172.25.5.28(App Server) to 172.25.15.121(DB Server) DB level - 10.5.9.20(LPC) to 172.25.15.121(DB Server) Network level - Internet Access enablement in 172.25.5.28(App Server) Network level | 9/13/2021 9/14/2021 9/19/2021 9/19/2021 | 9/13/2021 9/14/2021 9/19/2021 9/19/2021 | 100% | Following access given based on Micromac team requirement - Landing PC to App Server - Landing PC to DB server - App Server to DB Server - Internet Access in Test Server(Temporary)
|  | BBL (CBS - Shafayat) | Integration(Test) :: LMS to CBS (Customer, Owner and Guarantor Particulars for Loan) through direct API(SL-1) | 2021-09-13 | 2021-09-14 | 100%
|  | BBL (ADC - Shakib) | Integration(Test) :: LMS to ADC (Customer and Guarantor Particulars for Card) through query(SL-2) | 2021-09-13 | 2021-09-13 | 100% | OmniCard DB Info: Nazmus Shakib: Mon 9/13/2021 3:09 PM Omnicard UAT BOS db IP: 172.25.15.45 port : 1522 Username: LMS02 DB IP: 172.25.15.45 Service Name: bosprod
|  | BBL (CBS - Shafayat) | Integration :: LMS to CBS (Loan Facility Details) via API(SL-3) | 2021-09-13 | 2021-09-15 | 100% | Requirement: 1. od_acct_inq (OD Account) request/response templates. 2. Current_acct_inq (Current Account) request/response templates. 3. An API (List of Accounts in a CIF) is required to identify account schema types (Loan, OD, Current). Date: 22/09/2021 API share By Shakil Bhai(ADES) WSDL: https://172.25.0.5:4444/UBA/LoanListAndDetails/V1?wsdl WSDL: https://172.25.0.5:4444/UBA/CasaListAndDetails/V1 API Name: • Loan List and Details-OD against CASA ( Need both API and Credentials ) • Loan details API (Need only Credentials as API already shared by you earlier)
|  | BBL (ADC - Shakib) | Integration :: LMS to ADC (Card Facility Details) through query(SL-4) | 2021-09-13 | 2021-09-13 | 100% | OmniCard DB Info: Nazmus Shakib: Mon 9/13/2021 3:09 PM Omnicard UAT BOS db IP: 172.25.15.45 port : 1522 Username: LMS02 DB IP: 172.25.15.45 Service Name: bosprod
5 |  | BBL(Core System-Kawsar) | Live Environment Readiness :: Application Server Readiness Test Server details: IP:10.5.21.20 User:appuser Directory:/app Port Details: VA & Mitigation: | 2021-09-30 |  |  | To ensure the 1st phase delivery by Sep 30 following APIs need to be delivered by Sep 13, 2021. If you have any observations regarding the schedule please let us know. API list: 1. Customer [Loan, Card] 2. Owner [Loan, Card] 3. Guarantor [Loan, Card] 4. Facility Details [Loan, Card] As per bank decision the POC server will be used as UAT server.
|  | BBL | Live Environment Readiness :: Database Server Readiness DB Server details: DB Name: lmsdb Username: lms DB IP: 172.25.15.121 DB Port: 3489
Landing PC to Server Connectivity :: - 10.5.9.20(LPC) to 172.25.5.28(App Server) Network level - 172.25.5.28(App Server) to 172.25.15.121(DB Server) DB level - 10.5.9.20(LPC) to 172.25.15.121(DB Server) Network level
|  | BBL (CBS - Shafayat) | Integration(Test) :: LMS to CBS (Customer, Owner and Guarantor Particulars for Loan) through direct API(SL-1) | 2021-09-23 | 2021-09-14
|  | BBL (ADC - Shakib) | Integration(Test) :: LMS to ADC (Customer and Guarantor Particulars for Card) through query(SL-2) |  | 2021-09-13
|  | BBL (CBS - Shafayat) | Integration :: LMS to CBS (Loan Facility Details) via API(SL-3) |  | 2021-09-15
|  | BBL (ADC - Shakib) | Integration :: LMS to ADC (Card Facility Details) through query(SL-4) |  | 2021-09-13
6 | System Design & Readiness (Phase-1) | MICROMAC | Test - OCI Configuration - PHP installation & - Others | 2021-09-23 | 2021-09-23
|  | MICROMAC | Live - OCI Configuration - PHP installation & - Others | 2021-09-28 |  |  | On-Progress
7 | UAT Release of 1st Phase Deliverables | MICROMAC |  | 2021-09-28 | 2021-09-28 |  | 1st Phase Deliverables: - Legal Notice - CMA Approval (without auction feature)
8 | Bank's feedback on 1st Phase Delivery | BBL |  | 2021-09-30 | 2021-10-03 |  | MicroMac's expectation is Sep 30, 2021. If bank has any observation regarding the schedule then they are requested to inform MicroMac.
9 | UAT Release of 1st Legal Notice (1st Phase) Deliverables | MICROMAC |  | 2021-10-11 | 2021-10-11
10 | Bank's feedback on 1st Legal Notice (1st Phase Delivery) | BBL |  | 2021-10-12 | 2021-10-12
11 | UAT Release of CMA (1st Phase) Deliverables | MICROMAC |  | 2021-10-13 | 2021-10-13
12 | Bank's feedback on CMA (1st Phase Delivery) | BBL |  | 2021-10-14 | 2021-10-14
13 | Phase-1 Live | BBL & Micromac |  | 9/30/2021 10/18/2021 12/28/2021 |  |  | Live with two modules - Legal Notice - CMA Approval with auction feature)
Final Phase
14 | API requirements finalization of Final Phase | MICROMAC, BBL |  | 2022-01-13
15 | API documents share of Final Phase | BBL |  | 2022-01-31 |  |  | BBL is requested to put the date.
16 | Scope of Data Migration | MICROMAC, BBL |  | 2022-01-31
17 | Share Pending Issues of Phase-1 | BBL |  | 2022-01-10 |  |  | BBL is requested to put the date.
18 | Share format for data migration by MicroMac | MicroMac |  | 2022-02-17
19 | Data provided by Bank for data Migration | BBL |  | 2022-02-24 |  |  | BBL is requested to put the date.
20 | Development of Final Phase | MICROMAC |  | 2022-05-12
21 | Testing on Final Phase | MICROMAC |  | 2022-05-18
22 | UAT Release of Final Phase | MICROMAC | Data Migration (dummy) | 2022-05-19
23 | UAT Training on Final Phase | MICROMAC, BBL
24 | Conduct UAT on Final Phase | BBL |  |  |  |  | BBL is requested to put the date.
25 | UAT Issues Fix Delivery | MICROMAC |  |  |  |  | MicroMac will share the date after receive the completion of UAT date.
26 | Re-Check Issue | BBL |  |  |  |  | BBL is requested to put the date.
27 | UAT Sign-off & Implementation Authorization | BBL |  |  |  |  | BBL is requested to put the date.
28 | Data Migration | MICROMAC |  |  |  |  | MicroMac will share the date after receive the completion of UAT date.
29 | Production Release and GOLIVE | MICROMAC, BBL |  |  |  |  | BBL is requested to put the date.

## API
SL | Module Name | API Name | working-Days | Remarks
1 | Month-wise Statement -Loan MBS |  | 2 | # before 4/12/2007 # ac no 16-14 formula# manual
2 | Month-wise Statement -Loan XCRV |  | 2 | LOAN Liability Statement
3 | Month-wise Statement -Card | CardPro | 2 | Query received
5 | Bills Processing- status | Finance ERP | 2 | Lawyer/Vendor Account number, Lawyer/Vendor Invoice OR other Reference Number
8
Manual+CBS There are 3 ways to generate a statement as described below: a. MBS data [12 digits A/C #] [Data needs to be reordered][till 12 April 2007 b. XCRV Data [16 digits A/C #] c. Manual Calculation: >> Up to 31March2020 use sanction rate, from 1April2020 use 9%. >> Interest accrued should not exceed 200% of the principal amount. >> Up to specific data, BBL will share account wise monthly recovery amount. We will take the recovery amount (date wise) from the XCRV from the specific date

## Module
SL | Module Name | Status | working-Days | Remarks
1 | 1st LN | Done
2 | CMA | Done
3 | Auction | Done
4 | Statement |  | 10 | API
5 | Suit Filing and Legal Action |  | 10
6 | Bills Processing |  | 5 | API
7 | AIT & VAT Certificate |  | 5
8 | Warrant of Arrest |  | 5
9 | Appeal & Bail Money |  | 8
10 | HC Matters |  | 10
11 | Case against Bank |  | 10
12 | Vetting Checklist & Deed of Mortgage, Deed of Power, Redemption, Cancellation |  | 0 | out of scope
13 | Reports |  | 10
14 | Legal Affairs |  | 5
15 | Reminder |  | 10
16 | Data Migration |  | 10
17 | Court/Others Documents Upload |  | 2
100
|  | API | 8
| BBL will share existing live modules gap | Live Module | 10
|  | working date | 118

## Team
BRAC Bank Limited
Designation | Name | Mobile No. | Email
Functional Project Manager | Sabbir Abedin | 01730704768 | sabbir.abedin@bracbank.com
| Ossaed Ahmed | 01777701529 | ossaed.ahmed@bracbank.com
Technical Project Manager | Mir Mohammad Asiful Bari | 01711082952 | mirasiful.bari@bracbank.com
| Golam Rabbany | 01711082104 | mdgolam.rabbany@bracbank.com
Technical Project Members | Sumit Roy | 01713659237 | sumit.roy@bracbank.com
| Abu Syeed Muhammad Al Mustofa | 01787653566 | a.syeed@bracbank.com
| Masuqur Rahman | 01730704674 | mdmasuqur.rahman@bracbank.com
| Shakil Ahammad | 01847196236 | shakil.ahammad@bracbank.com
| Rubayet Hasan | 01713481120 | mdrubayet.hasan@bracbank.com
| Shohag Sarker | 01713493987 | shohag.sarker@bracbank.com
| Ikhtear Uddin Bilash | 01714097721 | kiu.bilash@bracbank.com
| Nasimuzzaman | 01847431980 | Nasimuzzaman.30057@bracbank.com
| Aman Ullah Sarker | 01701209044 | aman.sarker@bracbank.com
MicroMac Techno Valley Limited
Designation | Name | Mobile No. | Email
Project Manager | Md. Hosain Ahmed | 01961641250 | hosain@mmtvbd.com
Team Member | Ha-Mim Hyder | 01799333823 | ha.mim@mmtvbd.com
| Md. Enayet Ullah | 01903181082 | enayet.ullah@mmtvbd.com

## Progress
LMS Working Progress
SL | Milestones | Actual % Work Progress | Remarks
1 | Login Page/Form | 100%
2 | Forgot Password Process | 100%
3 | Landing Page | 100%
4 | User Group Management | 100%
5 | User Management | 100%
Basic Parameters
6 | Country | 100%
7 | Segment Type | 100%
8 | Currency | 100%
9 | Department | 100%
10 | Designation | 100%
11 | Month | 100%
12 | Option | 100%
13 | Remittance Status | 100%
14 | Educational Qualification | 100%
15 | Level of Degree | 100%
16 | Code Type | 100%
17 | District | 100%
18 | GL Type | 100%
19 | GL List | 100%
20 | Swift Name | 100%
21 | Swift Charge | 100%
22 | Zone | 100%
23 | Payment Mode | 100%
24 | Agency Setup | 100%
25 | Account Wise BIDA/EPZ | 100%
26 | TAX Section | 100%
27 | Branch Management | 100%
28 | NGO Project | 100%
29 | NGO Project Approval Management | 100%
30 | NOSTRO Account Setup | 100%
31 | NOSTRO Charge Setup | 100%
32 | Purpose Code | 100%
1 | Suit Filing and Legal Action | 95%
34 | Cost Center | 100%
35 | Schema Code/ Description | 100%
36 | Certificate Charge Setup | 100%
37 | Charge Setup | 100%
| GL List | 100%
38 | TAX Challan | 100%
INWARD
39 | SWIFT message load: | 100%
40 | MT-103 Process | 100%
41 | Process | 100%
42 | Inward Common Queue | 100%
2 | Bills Processing | 80%
3 | AIT & VAT Certificate | 95%
49 | Inward Incentive Common Queue | 100%
50 | Inward Incentive Self Queue | 100%
51 | BB FROM-C XML | 100%
52 | Encashment Certificate | 100%
53 | Credit Advice Certificate | 100%
54 | AD Certificate | 100%
55 | TAX Certificate | 100%
57 | Corporate Email | 100%
58 | Query Queue | 100%
Entity
59 | Entity Common Queue | 100%
60 | Entity Self Queue | 100%
Outward
61 | Outward Common Queue | 100%
62 | Outward Self Queue | 100%
63 | Checker Approve | 100%
65 | Checker Return | 100%
66 | Check Print Status | 100%
68 | Un-LIEN Status Update | 100%
69 | TM data create for Corresponding Bank Charge | 100%
70 | BB TM XML | 100%
71 | Debit Advice Certificate | 100%
72 | Tax Certificate | 100%
73 | VAT Certificate | 100%
Documentation
75 | Document Management | 100%
Report
|  |  | Modules | Completed | Remaining
| Average | 97.69% | Suit Filing and Legal Action | 95% | 5%
|  |  | AIT & VAT Certificate | 95% | 5%
| Remaining | 2.308% | Bills Processing | 80% | 20%
|  |  | Entity Module | 98% | 2%
|  |  | Outward Module | 80% | 20%
|  |  | Inward Module | 50% | 50%
|  |  | Cancellation Module | 0% | 100%
|  |  | Documentation Module | 100% | 0%
|  |  | Report & Dashboard | 0% | 100%
|  |  |  | 66.44% | 33.56%
[6 empty] | Completed | 95%
[6 empty] | Remaining | 5%